## Sheet1
Milestone Name | Details | Design time | Development time | Api creation time | Date
Home page | header banner store products trending products api implemantation and creation | 3,4 Days With Tabs and Menus | 2 days | 2 days | 2023-08-18
welcome screen | page creation | 1 day |  |  | 2023-08-21
OTP page | page creation, Api integeration otp verification api creation | 1 days | 2 days | 2 days | 2023-08-25
Add address page | page creation, Api integeration, search implementation, edit functionality add and show address api creation and implementation | 2 days | 4 days | 4 days | 2023-09-06
Add payment page | add and show address api creation and implementation page design, payment gateway imlementation | 1 Days | 7 days | 7 days | 2023-09-19
Review cart | page design, cart list api and Saved For later api creation and implementation Apply coupon Api creation implemantation address and cancellation policy api | 2 days | 4 days | 4 days | 2023-09-27
Product Detail page | page design, product detail api, related product api, user reviews api user recipe api write review api bookmark product api add to cart functionality implementation and creation | 3 days include with View cart Button | 5 days | 5 days | 2023-10-06
view cart button | page design
Explore by category | page design add to cart functionality product list api by category | 2 days | 2 days | 2 days | 2023-10-12
subcategory page | page design product list api by subcategory subcategory list api add to cart functionality | 2 days | 3 days | 3 days | 2023-10-20
Forget password page | page design Forget password api implementation and creation | 1 days | 1 days | 1 days | 2023-10-24
login page | page design login api social login api implementation and creation | 1 days | 3 days | 3 days | 2023-10-30